EPOS-GNSS Consortium Board Action Items									                         Last updated: October 2025

| Action Item |  | Responsible Person or Group | Projected Completion Date | Status as of Oct 16, 2025 | Comments |
| --- | --- | --- | --- | --- | --- |
| 14th CB meeting – 24-25 Sept. 2025 – Grenoble and Teleconference |  |  |  |  |  |
| 14-1 | Distribute the new web content to the partners for commenting. | João Lima, Rui | October 15 | In progress |  |
| 14-2 | Lead the discussions with NOA and DGW to implement new station names and rename the RINEX files for the three Bulgarian stations. | Jean-Luc |  |  |  |
| 14-3 | Update the products portal to allow users to filter offsets by date, event, or station. | Rui, Fernando |  |  |  |
| 14-4 | Report the CB meeting minutes to the Data Providers Committee and engage more with them. | Karin Kollo |  |  |  |
| 14-5 | Select the most important questions raised by the members and forward them to the User Feedback Group for input. | Jeff Freymuller |  |  |  |
| 14-6a | Write a formal announcement to the CB for her with withdrawal | Mathilde |  | Done |  |
| 14-6b | Write a formal acknowledgment to the Directors of OCA and EPOS France about Mathilde leaving, noting there is no replacement and the position is open. Then ask EPOS France about the consequences and replacement plans. | Rui |  | Done |  |
| 14-7 | Organize webinars and short meetings on scientific and technical topics, 1–2 hours each, to be held 3–4 times per year. | Rui, João |  |  |  |
| 14-8 | Invite Nikolay Dimitrov to be the Co-Chair of the Data Provider Committee, for him to be able to participate CB meetings without signing the Consortium Agreement. Ask Nikolay to contribute with fostering contributions from the Balkan region. | Rui |  | Done |  |
| 14-9 | Rui will represent EPOS in the discussions with EarthScope and GFZ regarding TileDB, focusing on the standardization of file usage. | Rui |  | In progress |  |
| 14-10 | Organize a discussion about the EPOS-GNSS provider license during the next software meeting, taking in account the EPOS data policy on licensing. | Jean Luc |  |  |  |
| 14-11 | INGV to provide dedicated solutions based on EPOS data and metadata, rather than a global solution. | Antonio |  |  |  |
| 14-12 | Decrease the delay for combined solutions in the EPOS products portal to less than one year. | Ambrus |  |  |  |
| 14-13 | Coordinate EPOS-GNSS group participation in the next EPOS Days with Lili. Once further details are available, Rui will distribute the information to all members. | Rui |  | In progress |  |
| 14-14 | Investigate if the members can declare node maintenance costs in the Costbook. | Rui |  | Done |  |
| 13th CB meeting – 9 Jan. 2025 – Teleconference |  |  |  |  |  |
| 13-1 | Send a letter to the EPOS-GNSS TCS formalizing their interest in joining the group. | José and Athanassis |  | Done |  |
| 13-2 | Create an Addendum draft with the inclusion of new members and distribute it to the CB | Rui |  | Done |  |
| 13-3 | Distribute the MYCA 2025 draft to CB for discussion and adjustments. | Rui |  | Done |  |
| 13-4 | Schedule a meeting with CB beneficiary members to discuss the delivery of MYCA 2025. | Rui |  | Done |  |
| 12th CB meeting – 26-27 Sep. 2024 – Brussels and Teleconference |  |  |  |  |  |
| 12-1 | Preparing a new webinar about TCS GNSS Data & Producs in 2025. | Rui |  |  |  |
| 12-2 | Promote a meeting with NIEP to discuss the maintenance of the Data node or the possibility of using another node to distribute the Romanian data. | Mathilde, Rui |  | In progress |  |
| 12-3 | Proceed with the incorporation of the IMO node at the EPOS infrastructure. | Mathilde, Rui |  | In progress |  |
| 12-4 | Implement a process to manage the creation of DOIs for the TCS data and products. | Carine |  | In progress |  |
| 12-5 | Add a link to the DQMS web site on the EPOS-GNSS landing pages | Rui |  | Done |  |
| 12-6 | Implement the Facility Registration for GNSS equipment linked to ICS. | Carine |  |  |  |
| 12-7 | Create a new service in ICS based on station metadata, to be maintained by ROB. | Carine |  |  |  |
| 12-8 | Setup a meeting to discuss which dedicated solutions must be created (and distributed) by the EPOS partners and if other solutions can also be made available. | Anne |  |  |  |
| 12-9 | Provide to Jeff functionalities on the EPOS data portal that we would like the UFG to test. | all |  |  |  |
| 12-10 | Evaluate the efforts to incorporate campaign data in EPOS. | Antonio, Carine, Mathilde |  |  |  |
| 12-11 | Send an email to partners requesting suggestions for improving the visibility of the EPOS website and collect the information before the next CB meeting to be discussed during the meeting. | Mathilde, all |  | Done |  |
| 12-12 | Invite the nodes to become a member of the TCS GNSS Consortium. | Rui |  | Done |  |
| 12-13 | Develop a strategic plan for incorporating new members into the Consortium. | all |  |  |  |
| 11th CB meeting – 10 June 2024 –Teleconference |  |  |  |  |  |
| 11-1 | Provide the template based on the information we have from MYCA 2024 for changes and additions. | Rui, Gabriela |  | Done |  |
| 11-2 | Informally contact the nodes by the end of September to ask if they are really interested (or not) in joining our TCS and schedule an extraordinary CB meeting to discuss this. | Rui |  | Done |  |
| 11-3 | Send by email to the entire CB by June 18th the questions to be discussed at the next SCC meeting. | all |  | Done |  |
| 11-4 | Make a list of the questions collected and distribute this for the CB by June 27th. | Rui, Gabriela |  | Done |  |
| 10th CB meeting – 20 Mar. 2024 –Teleconference |  |  |  |  |  |
| 10-1 | Interact with Polish colleagues via email to invite them for a next CB meeting. | Rui |  |  |  |
| 10-2 | Prepare and share a template document on Google Doc to insert information about available services to increase their visibility through the portal. | Mathilde, all |  |  |  |
| 10-3 | Create a Google Excel for the new Cost-Book and share for comments by April 4th. | Rui, all |  | Done | Excel shared on March 20 |
| 9th CB meeting – 2 Feb. 2024 –Teleconference |  |  |  |  |  |
| 9-1 | Find out when MYCA 2024 will be signed and inform everyone. | Rui |  | Done |  |
| 9-2 | Share the Cost-Book Excel on Google Sheet with other participants so that they can update the information in the document within two weeks. | Rui, all |  | Done |  |
| 8th CB meeting – 19-20 Oct. 2023 – Nice and Teleconference |  |  |  |  |  |
| 8-1 | Prepare the MYCA Work Program 2024. | all |  | Done |  |
| 8-2 | Coordinate the preparation of MYCA’s 2023 financial and activity reports. | Rui, Gabriela |  | Done |  |
| 8-3 | Begin the process of renewing CB and EB chair positions. | Rui, Gabriela |  | Done |  |
| 8-4 | Create a publicly available website for the INGV solutions so that DOI can be assigned to them. | Antonio, Luis and Rui Cardoso |  | In progress |  |
| 8-5 | Create guidelines for data providers. | Carine, Mathilde |  |  |  |
| 7th CB meeting – 14 Apr. 2023 –Teleconference |  |  |  |  |  |
| 7-1 | Start the process of purchasing airline tickets and booking accommodation for participants of the face-to-face CB meeting. | Rui and Gabriela | August | Done |  |
| 7-2 | Make available the TCS GNSS video that will be presented in the EGU to the participants. | Rui and Luis |  | Done |  |
| 7-3 | Establish a deadline for beginning full use of HTTPS by client web data distributors. | Mathilde & Juliette |  | In progress |  |
| 7-4 | Establish a procedure for what to do if the node fails to respond to a basic requirement. | All |  | In progress |  |
| 7-5 | Provide link to access the INGV solutions in the repository. | Rui |  | Done | Need to reconfigure the access or use the general url of the repository: https://gnssproducts.epos.ubi.pt/filemanager |
| 7-6 | Validate the new formats and work on importing the latest solutions. | Rui and Ambrus |  | Done |  |
| 7-7 | Initiate and manage the election process for management positions for the new mandate that will start in 2024. | Rui and Gabriela |  | Done | There was a consultation but no one expressed interest in taking over the management positions of EB and CB other than the current presidents. |
| 6th CB meeting – 29-30 Sep. 2022 – Lisbon and Teleconference |  |  |  |  |  |
| 6-1 | UBI will sign MYCA for Services and Products Provision as soon as final version is available. | Rui |  | Done |  |
| 6-2 | Consult UBI about distributing the money as soon as the contract with EPOS ERIC is signed. | Rui |  | Permanently in progress |  |
| 6-3 | Question EPOS ERIC if and when is planned to do an overall revision of the CostBook. | Rui |  | Done |  |
| 6-4 | Inform the Consortium Board about the interest of ROB to take the Coordination of Software development and, if positively, indicate the person. | Carine |  | Done |  |
| 6-5 | Work in partnership with the software group to improve data download by users. | Mathilde |  | Done |  |
| 6-6 | Create external committee(s) to review proposals if officially requested based on the topic of each proposal. | Rui |  | Permanently in progress |  |
| 5th CB meeting – 4 Mar. 2022 - Teleconference |  |  |  |  |  |
| 5-1 | Ask Lili if there will be any EPOS disclosure about the war in Europe. | Rui | Asap | Done |  |
| 5-2 | Make the EUREF MoU file available in word to Martin. | Rui | Asap | Done |  |
| 5-3 | Initiate contacts with interest groups to handle real-time GNSS positioning. | Antonio |  | In progress |  |
| 5-4 | Prepare a doodle for the fall face-to-face meeting. | Gabriela | Asap | Done |  |
| 5-5 | Prepare presentation for EUREF. | Carine | June 2022 | Done |  |
| 4th CB meeting – 24 June 2021 - Teleconference |  |  |  |  |  |
| 4-1 | Sends name of his proxy to CB. | Tomasz |  | Done | Doesn’t have a proxy! |
| 4-2 | Rui sends text of GNSS TCS contribution to SERV call to Fabrice Cotton. | Rui |  | Done |  |
| 4-3 | Rui sends around first draft of Special Issue on Annals of Geophysics article. | Rui |  | Done |  |
| 4-4 | Carine sends Juliette’s notes on how our TCS appears at the ICS website to EB. | Carine |  | Done |  |
| 3rd CB meeting – 27 October 2020 - Teleconference |  |  |  |  |  |
| 3-1 | Finalise formation of UFG and invite representatives to next CB meeting | Rui |  | Done |  |
| 3-2 | Distribute UFG 1-page description to CB. | Rui |  | Done |  |
| 3-3 | Set up DCP mailing list before 10 November. | UBI |  | Done |  |
| 3-4 | Until November 15 send outlines of webinar presentation. | CB |  | Done |  |
| 3-5 | Ask CB members for mailing addresses to announce the webinar. | Rui |  | Done |  |
| 3-6 | Move consortium board mail to EPOS intranet. | Rui |  | Done |  |
| 3-7 | Data Gateway and Product Portal managers should give a list of names/users to ICS who can test the TCS GNSS portals | Jean Luc and Machiel |  | Done |  |
| 3-8 | Setup a dedicated meeting with ICS in order to discuss TCS GNSS-ICS interaction. | Paul |  | Done |  |
| 3-9 | Inform CB when new minutes of EB meetings are online. | Machiel |  | Done |  |
| 3-10 | Paul presents to CB plan how to implement authentication at Data Gateway | Paul |  | Done |  |
| 3-11 | Set up meeting with Karin Kollo to discuss the future of the Estonian node | Rui |  | Done |  |
| 3-12 | Setup dedicated meeting to discuss EPOS-EUREF / EUREF-EPOS Densified solutions | Anne |  | Done |  |
| 2nd CB meeting – 26 June 2020 - Teleconference |  |  |  |  |  |
| 2-1 | All voting CB members should try to find a proxy (if possible). | CB |  | Done |  |
| 2-2 | Finish the 1-page UFG task description and organize meeting to discuss it. | Rui and Machiel |  | Done |  |
| 2-3 | Prepare description of how the Data Provider Committee will be organized | Carine |  | Done |  |
| 2-4 | Once meeting in Algarve is officially cancelled, set-up doodle to fix date of next CB meeting around 27 October | Rui |  | Done |  |
| 2-5 | Send the password of the site with the minutes to all the consortium board members | Machiel |  | Done |  |
| 2-6 | Iterate with EB on the criteria for new stations from proposed to active and then propose to CB. | Carine |  | Done |  |
| 1st EB meeting – 30 Jan. 2020 - Teleconference |  |  |  |  |  |
| 1-1 | Sends EPOS-SP proposal text to TCS. | Carine |  | Done |  |
| 1-2 | Write 1-page description of tasks of the User Feedback Group. | Rui |  | Done |  |
| 1-3 | Writes a description of how the Data Provider Committee will be organized. | Carine |  | Done |  |
| 1-4 | Sends the minutes of the Product meeting held on January 27. | Anne |  | Done |  |
| 1-5 | Write the outreach strategy for the coming year and distribute it for comments. | Rui and Machiel |  | Done |  |