EPOS-GNSS Executive Board Action Items									                         Last updated: March 24, 2025

| Action Item |  | Responsible Person or Group | Projected Completion Date | Status as of March 24, 2025 | Comments |
| --- | --- | --- | --- | --- | --- |
| 27th EB meeting – 24 March 2025 - Teleconference |  |  |  |  |  |
| 27-1 | Put EB in cc when discussing items related to other TCS. | M. Vergnolle |  |  |  |
| 27-2 | Send email to Nicolay Dimitrov to discuss setup of new Bulgarian node, put EB in cc. | J.-L. Menut |  |  |  |
| 27-3 | Announce EUREF symposium and Analysis Workshop to EPOS-GNSS community (encouraging participation) as well as EPOS ERIC communication team. | R. Fernandes |  |  |  |
| 27-4 | Coordinate participation of our TCS in relevant EGU sessions and splinter meetings. | R. Fernandes |  |  |  |
| 27-5 | Provide report on Vocabulary to EB for review. EB to provide feedback and send to R. Fernandes and J. Legrand for follow up. | J. Legrand & R. Fernandes |  |  |  |
| 27-6 | Present slides of new ICS services at software meeting. | A. Fabian |  |  |  |
| 27-7 | Propose use cases to be used for training purposes and increase usage of GNSS services at ICS. | G. Janex, EB |  |  |  |
| 27-8 | Discuss at software meeting improvement of service endpoints. | J. Legrand |  |  |  |
| 27-9 | Send email to chair of consortium board to inform about intention to step back as chair of the EB | C. Bruyninx |  | Done |  |
| 27-10 | Organise election of new co-chairs of the User Feedback Group | R. Fernandes |  |  |  |
| 27-11 | Organise fall meeting of Consortium Board | R. Fernandes |  |  |  |
| 26th EB meeting – 8 Nov. 2024 - Teleconference |  |  |  |  |  |
| 26-1 | Keep EB/CB informed about new developments related to upcoming EU calls. | R. Fernandes |  | Done |  |
| 26-2 | Organise extra-ordinary CB meetings in Dec. 2024 and January 2025 to discuss MYCA funding in 2025. | R. Fernandes |  | Done |  |
| 26-3 | Insert metadata curators in https://epos-ci.brgm.fr/ics-tcs/epos-dcat-ap/tcs-data-service-providers/-/blob/main/metadata-curators-contacts.md (Luis for backoffice tool, Juliette for vocabulary, Anna Miglio for DOI). | R. Fernandes L. Carvalho |  | Done |  |
| 26-4 | Inform EPOS ERIC communication office that Cintia will replace Gabriela. | R. Fernandes |  | Done |  |
| 26-5 | Send email about DMP survey to Anne and EB. | C. Bruyninx |  | Done |  |
| 26-6 | Ask agencies that provide products to fill in DMP questionnaire. | A. Socquet |  | Done |  |
| 26-7 | Send GNSS-related slides of Corinth summer school to EB. | A. Socquet |  | Done |  |
| 26-8 | Put slides provided by Anne on EPOS-GNSS web site. | L. Carvalho |  | Done |  |
| 26-9 | Propose new structure for EPOS-GNSS web site. | C. Bruyninx |  | In progress |  |
| 26-10 | Add links to 4 community portals to EPOS-GNSS web site. | L. Carvalho |  | Done |  |
| 25th EB meeting – 29 Apr. 2024 - Teleconference |  |  |  |  |  |
| 25-1 | Harmonize the links that are visible on the EPOS software page (https://gnss-epos.eu/software-developers/). | R. Fernandes L. Carvalho |  | Done |  |
| 25-2 | Organise fall CB meeting | R. Fernandes G. Batti |  | Done |  |
| 25-3 | Include on the agenda of next CB meeting a discussion topic about how our community portals can be improved to enhance the visibility of all partners (see also CB AI 10-2). | G. Batti |  | Done | Agenda topic B.2 – CB meeting in Brussels |
| 25-4 | Provide administrative information to all MYCA partners | R. Fernandes |  | Permanently in progress |  |
| 25-5 | Update the EPOS data supplier letter to reflect need for http(s) access to data | C. Bruyninx |  | Done | Done on 02-05-2024 |
| 24th EB meeting – 02 Feb. 2024 - Teleconference |  |  |  |  |  |
| 24-1 | Distribute again documents related to AI 22-4 so that EB can comment | R. Fernandes + all |  | Done | On 09-05-2024 Gabriela sent the google doc to CB email list. On the same day she sent an email to Federica and there was an exchange of emails on this subject between them and Rui. On 16-05-2024 Carine suggested to Rui to put the topic up for discussion at the SSC meeting. obsolete, taken over by EPOS ERIC communication team |
| 24-2 | Set up a doodle to organise a spring CB meeting after the EPOS days | R. Fernandes |  | Done |  |
| 24-3 | Inform NOA about discussions with CRL | M. Vergnolle |  | Done | April 12th 2024 : to EB April 17th 2024 : to NOA |
| 24-4 | Create web page with form that allows people to register for general TCS mailing list + send email around (to e.g. DPC) to inform users about new mailing list | L. Carvalho, R. Fernandes |  | Done |  |
| 23th EB meeting – 17 Nov. 2023 - Teleconference |  |  |  |  |  |
| 23-1 | Coordinate the revision of the cost book | R. Fernandes + all |  | Done |  |
| 23-2 | Set up date for CB meeting in Febr. 2024 | R. Fernandes |  | Done |  |
| 23-3 | Inform CB of EPOS days (11-15 March 2024) | R. Fernandes |  | Done |  |
| 23-4 | Prepare the Activity Plan in the framework of the MoUs with EUREF and EUMETNET | R. Fernandes C. Bruyninx |  | Done | Activity Plan with EUREF done - signed. Contact with EUMETNET is being established. |
| 23-5 | Send the announcement of the EPOS session at EGU 2024 to the CB members | R. Fernandes |  | Done |  |
| 23-6 | Send the node meeting notes to EB | M. Vergnolle, |  | Done | Sent March 4th 2024 |
| 23-7 | Clarify permissions to distribute data of Corinth stations | M. Vergnolle, C. Bruyninx |  | Done | (1) no global NFO node planned. GNSS stations for other NFOs (Italy, Romania) belong to one partner only and transit through the existing partner node. (2) CRL is an international partnership NFO. |
| 23-8 | Discuss evolution of EPOS GNSS data products and report at next CB | A. Socquet |  | In progress | Report at next CB |
| 23-9 | Organise meeting to discuss software for distribution of high-rate data with software group and Geo-Inquire group, report to EB | M. Vergnolle, J. Legrand |  | Done |  |
| 23-10 | Update document with the tasks of the coordinators | All coordinators | 2 weeks before next EB meeting | In progress |  |
| 23-11 | Put on agenda of future EB: Discussion about general EPOS-GNSS mailing list | R. Fernandes |  | Done |  |
| 22th EB meeting – 08 Sept 2023 - Teleconference |  |  |  |  |  |
| 22-1 | Finalise organisation CB | M. Vergnolle, R. Fernandes |  | Done |  |
| 22-2 | Clarify with EPOS ED the issue of having TCS booth at EGU and AGU | R. Fernandes |  | Done |  |
| 22-3 | Provide link to communications web page to EB/CB and ask to check and complete | G. Batti |  | Done |  |
| 22-4 | Provide word document with proposal for updating https://www.epos-eu.org/tcs/gnss-data-and-products to EB. EB provide feedback before sending document to EPOS communication office (TCS take off pages to be updated in next step) | R. Fernandes |  | Done | All to provide feedback on word document provided by RF obsolete |
| 22-5 | Provide list of stations whose data are available from ROB-EUREF and pan-European node to ROB and UBI | M. Vergnolle |  | Done | Mail sent on 29/04/2024 |
| 22-6 | Organise discussion with CRL to find existing EPOS-GNSS node for their data. Contact NOA to inquire about their willingness to add CRL data in their EPOS node. | M. Vergnolle, R. Fernandes |  | Done | NOA agreed already / Meeting on January 26th, 2024. Issue to be solved on the CRL side + open question to EPOS-GNSS |
| 22-7 | Contact UFG to find volunteers to regularly check TCS data and product portals | R. Fernandes |  | Done | Jeff Freymuller provided feedback. No other replies |
| 21th EB meeting – 11 May 2023 - Teleconference |  |  |  |  |  |
| 21-1 | Update EPOS-GNSS web site to add recent presentations | R. Fernandes, G. Batti |  | Done | All provide info about presentations |
| 21-2 | Send email to EB/CB to ask them to look at our TCS web pages at the EPOS ERIC web site (and provide the link to the web pages). | R. Fernandes, G. Batti |  | Partly done, new AI 22-4 | All to provide feedback |
| 21-3 | Check if software meeting can be held in conjunction with CB meeting in Nice | M. Vergnolle, J. Legrand |  | Done |  |
| 21-4 | Ask EPOS ERIC is they provided the remaining 30% of the budget of the two 2022 MYCAs to EPOS ERIC | R. Fernandes |  | Done |  |
| 21-5 | Create a group to discuss the evolution of services at ICS (IT+scientists) | L. Carvalho, R. Fernandes |  | Done | Created - ics-gnss@gnss-epos.eu - To be discussed who should be invited to be member. |
| 21-6 | Create a group to discuss use of Jupyter Notebook (ICS-D) | J. Legrand, A. Fabian, L. Carvalho |  | Done | Group created |
| 20th EB meeting – 28 Feb. 2023 - Teleconference |  |  |  |  |  |
| 20-1 | Check content of EPOS landing page at UBI and provide feedback to Rui | All |  | In progress | Provide Feedback by email! CB: missing presentations 17/11/2023: put this on hold and work first on 22-4 |
| 20-2 | Schedule date(s) and decide about location(s) of software development meeting(s) | J. Legrand and P. Crocker |  | Done | Suggestion to have first an on-line FWSS meeting (alternative in Rome or Nice). Second meeting focussing on API, database, and synchronisation to be held at UBI. |
| 20-3 | Provide name of 2 new people at UBI that will work on API and database to J. Legrand | P. Crocker |  | Done |  |
| 20-4 | Provide name of M. Vergnolle who will be participating to the EGU to the EPOS communication office | R. Fernandes | URGENT | Done |  |
| 20-5 | Distribute last update of the technical action items to EB before each EB meeting. | M. Vergnolle, A. Socquet, J. Legrand | Recurrent |  |  |
| 20-6 | Send email with the link to the ICS Implement level matrix to the EB for revision | R. Fernandes, All |  | Done |  |
| 20-7 | Put acceptance of EPOS-GNSS data quality monitoring web site as a community portal on agenda of CB | C. Bruyninx |  | Done |  |
| 20-8 | Ensure that the new solutions submitted to the product portal become discoverable and downloadable from ICS | R. Fernandes |  | Done |  |
| 19th EB meeting – 23 Jan. 2023 - Teleconference |  |  |  |  |  |
| 19-1 | Finish annual report of MYCA on governance and coordination. | All parties of MYCA | End of Jan. 2023 | Done | Activity reports finished |
| 19-2 | Finish annual report of MYCA on data and service provision. | UBI+ All parties of MYCA | End of Jan. 2023 | Done | Activity reports finished |
| 19-3 | Inform parties when UBI transforms money (related to the MYCA) to them. | UBI | Permanent activity | In progress | Need explicit info on when money was transferred. |
| 19-4 | Check status of signature of 2022 third-party agreement with CNRS | UBI | Urgent | Done |  |
| 19-5 | Make doodle to fix the dates of a spring and fall consortium board meeting, fix dates, and inform CB. | G. Batti | ASAP | Done | Spring meeting scheduled for April 14th. To discuss the other date there will be a meeting between UBI and Mathilde on March 1st. |
| 19-6 | Organize fall CB meeting. | M. Vergnolle & R. Fernandes |  | Done |  |
| 19-7 | Put on agenda of CB: procedure when node fails responding to EPOS requirements? | M. Vergnolle |  | Done | Conclusion: Bi-lateral discussion with node required, led by manager of node infrastructure. |
| 19-8 | Split and update technical action items (one for data, one for products, and one for software) and provide them to G. Batti (and EB) | M. Vergnolle, J. Legrand, G. Batti |  | Done |  |
| 19-9 | Inform EPOS nodes that EPOS reprocessing will start in summer 2023 so that they make sure their data are as complete as possible | M. Vergnolle |  | Done |  |
| 19-10 | Discuss with software team the possibility to organize a face-to-face development meeting of one week. | J. Legrand |  | Done | Agreement on usefulness of development meeting, but optimal timing still to be agreed upon. To decide if 1 or 2 meetings will be organised. |
| 19-11 | Ask managers of EPOS-GNSS partners if they have budget for their members to attend software development meeting. | R. Fernandes |  | Done | All partners have budget for 1 travel. Organise meeting in conjunction with CB in Nice? |
| 19-12 | Ask to put on agenda of next CB meeting the topic ‘Geographical requirements of EPOS stations’ and prepare the item for presentation at the CB. | M. Vergnolle |  | Done | Conclusion: No geographical limit. CB to put it on agenda SCC meeting |
| 18th EB meeting – 25 Oct. 2022 - Teleconference |  |  |  |  |  |
| 18-1 | Send MYCA for data provision to the concerned third parties. | R. Fernandes |  | Done |  |
| 18-2 | Ask EPOS ECO to provide information on when it will send MYCA related money to UBI and then inform the third parties involved. | R. Fernandes & G. Batti |  | Done |  |
| 18-3 | Check CB procedure to appoint TCS representative to the SCC. | R. Fernandes |  | Done |  |
| 18-4 | Make available the merged document with the responsibilities of the coordinators from the EPOS-GNSS landing web site. | UBI |  | Done |  |
| 18-5 | Put a link on the home page of the product portal to point directly to the descriptive overview of the products. | L. Carvalho & G. Janex |  | Done (on development portal) |  |
| 18-6 | Rediscuss how to make WUT solution available from ICS in 2023. | All |  | Not done | To be discussed Tomasz L., after in CB |
| 18-7 | Update node installation instructions. | L. Carvalho, J.L. Menut & J. Legrand |  | Permanently in progress | LC: to update documents with new explanations that have been provided by email - LC takes over from PC (17/11/2023). JLM sent on April 19th 2024 some update to integrate in the guidelines to the software list (formatted google doc share document) |
| 18-8 | Maintain new separate list of AI related to software, independent from EB AI list. | J. Legrand |  | Done |  |
| 18-9 | Check our TCS info (content!) on EPOS web site and propose, if necessary, improvements. | All |  | NEW AII | Concerns EPOS ERIC web site. Send input to G. Batti and R. Fernandes |
| 18-10 | Prepare the doodle for the next EB meeting. | G. Batti |  | Done |  |
| 18-11 | Check the dates for submission of MYCA reports to the EPOS ECO and inform concerned partners. | R. Fernandes & G. Batti |  | Done |  |
| 17th EB meeting – 02 Sept. 2022 - Teleconference |  |  |  |  |  |
| 17-1 | Finalise agenda of CB meeting on Sept. 29, 2002 | R. Fernandes | 05-09-2022 | Done | Urgent |
| 17-2 | Provide participants to CB meeting info on hotel/meeting place, how to travel from hotel to meeting place, clarify reimbursement rules (email) | R. Fernandes & G. Batti | 25-09-2022 | Done |  |
| 17-3 | Finalise input to VA MYCA and send it to EPOS ECO | R. Fernandes | 07-09-2022 | Done | Urgent |
| 17-4 | Clarify if signature third-party agreements to MYCA are mandatory or not (for EPOS ECO and each party) | R. Fernandes & all | ASAP | Done |  |
| 17-5 | Ask EPOS ECO if they will organise session about EPOS at EGU | R. Fernandes | ASAP |  | Not relevant anymore |
| 17-6 | Organise meeting with software developers as follow up of March 29, 2022 meeting | J. Legrand & P. Crocker | Oct. 2022 | Done |  |
| 17-7 | Distribute minutes of 1st node meeting to EB and nodes | M. Vergnolle | ASAP | Done |  |
| 17-8 | Prepare presentation on duplicate RINEX at one node and data available from multiple nodes for CB | J.L. Menut & J. Legrand | By CB meeting 29 Sept. 2022 | Done |  |
| 17-9 | Meeting between ROB and DGW to discuss how to organise work related to nodes | J. Legrand & M. Vergnolle | ASAP | Done |  |
| 17-10 | Organise meeting with all nodes individually as follow-up of spring meeting | J. Legrand | Fall 2022 | Done |  |
| 16th EB meeting – 19 April 2022 - Teleconference |  |  |  |  |  |
| 16-1 | Inform EB about Paul's availability on May 5th and 6th. | R. Fernandes |  | Done |  |
| 16-2 | Adapt the workshop schedule according to support availability. | All |  | Done |  |
| 16-3 | Inform workshop participants about the planned schedule. | R. Fernandes |  | Done |  |
| 15th EB meeting – 09 March 2022 - Teleconference |  |  |  |  |  |
| 15-1 | Send updated MoU EUREF-EPOS that was approved by the Consortium Board to the chair of EUREF | R. Fernandes |  | Done |  |
| 15-2 | Create a google doc and put ideas for organisation and participants to the May 5-6 technical workshop in the google doc | R. Fernandes & All |  | Done | It was created by Rui, but it is needs everyone's contribution. |
| 15-3 | Organise extraordinary EB meeting (end of March – beginning of April) to prepare organisation of May 5-6 technical workshop | G. Batti |  | Done |  |
| 15-4 | Send “save the date” email to node managers to inform them about May 5-6 technical workshop | M. Vergnolle |  | Done | It was done on March 15th. |
| 15-5 | Send “save the date” email to User Feedback Group to inform them about May 5-6 technical workshop | R. Fernandes |  | Done |  |
| 15-6 | Add J.-L. Menut to Executive Board mailing list | R. Fernandes |  | Done |  |
| 15-7 | Make annual report 2021 of MYCA on Governance and Coordination available on EPOS-GNSS landing web site (in restricted zone) | R. Fernandes |  | Done |  |
| 15-8 | Take initiative to hold regular (~monthly) meetings between UGA and UBI to discuss development of product portal | G. Janex |  | Done |  |
| 14th EB meeting – 14 Jan. 2022 - Teleconference |  |  |  |  |  |
| 14-1 | Make the MoU between EUREF and EPOS available on Google Drive and share the link with the EB via email. | R. Fernandes |  | Done |  |
| 14-2 | Share the editable Activity Report of 2021 for the MYCA on Governance and Coordination online with the EB. | R. Fernandes & G. Batti |  | Done |  |
| 14-3 | Create a new doodle and set the date for the 1st annual CB online meeting. | R. Fernandes & G. Batti |  | Done |  |
| 13th EB meeting – 09 Dec. 2021 - Teleconference |  |  |  |  |  |
| 13-1 | Send MYCA for governance and coordination to EPOS ECO | R. Fernandes | urgent | Done |  |
| 13-2 | Ask ECO about template/signatures expected by ECO for annual report for MYCA on governance and coordination and provide instructions to EB | R. Fernandes & G. Batti | urgent | Done |  |
| 13-3 | Provide input for annual report of MYCA on governance and coordination (as soon as 13-2 is done) | All involved in MYCA | Feb. 1, 2022 | Done |  |
| 13-4 | Organise doodle for EB (+ relevant technical staff) meeting about ICS | G. Batti |  | Done |  |
| 13-5 | Have meeting in 13-4 and agree on strategy to update ICS documentation and other stuff (after 13-4) | All |  | Done |  |
| 13-6 | Ask Paul to report about testing of Anubis and provide recommendation to JL if nodes can use start using new Anubis | R. Fernandes |  | Done |  |
| 13-7 | Provide feedback about EUREF-EPOS MoU to CB | All |  | Done | MoU to be iterated/agreed upon by EB before next CB meeting |
| 13-8 | Set up doodle for CB meeting early 2022 | R. Fernandes & G. Batti |  | Done |  |
| 13-9 | Decide on date of physical CB (+ extended) meeting late spring and send “save the date” mail to participants | R. Fernandes & G. Batti |  | Done |  |
| 12th EB meeting – 22 Oct. 2021 - Teleconference |  |  |  |  |  |
| 12-1 | Prepare overview for users of which products can be used for what (to be put in EPOS-GNSS paper and put also on product gateway) | A. Socquet |  |  | This document might not yet reflect what is currently available from the PGW |
| 12-2 | Finish technical description of products to be published on PGW | A. Socquet |  | Done | To replace EPOS-IP deliverable on PGW |
| 12-3 | Iterate with EB to have work plan for 2022 for MYCA for Governance and Coordination ready by Nov. 22 | R. Fernandes |  | Done | Before Nov. 22!!! |
| 12-4 | Set up meeting between UBI and A. Socquet/J. Legrand to discuss way forward for PGW + Report at EB | R. Fernandes & P. Crocker |  | Done | March 10, 2022 Station metadata, response time |
| 12-5 | Inform EPOS-GNSS CB about latest evolutions about Service Activation | R. Fernandes |  | Done | Updated on December, 6 |
| 12-6 | Discuss how to deal with “stations with RINEX data” on ICS (meeting DGW, M3G, UBI) | all |  | Done | End of Nov. (email send by Mathilde – 9/12/2021) |
| 12-7 | Investigate how to back-up the whole EPOS GLASS network and a node | J.L. Menut |  | Done | A group was set up to think about that question (cf 1st node meeting minutes). A meeting has to be organized (JLM). Add to node guidelines that nodes need to have backup system in place. JLM organized a meeting on 2022-11-29, summary of the meeting online in the Node share directory, Node guidelines were updated (dump everyday required) |
| 12-8 | Meeting between software developers involved in EPOS-GNSS | P. Crocker |  | Done | Meeting held in Dec. 2021 Add Antonio to mailing list |
| 12-9 | Report at next EB on meeting about GLASS software versioning (needed to set up strategy document on procedure for updating GLASS) | P. Crocker & J.L. Menut |  | Done | Meeting held at 29 Oct. 2021, versioning standard is selected (major.minor.patch) and discussion on update strategy |
| 12-10 | Prepare a document with a strategy for upgrading GLASS | P. Crocker & J.L. Menut |  | Closed | Report at next EB! |
| 12-11 | Videos EPOS-GNSS general & M3G to be finalized | T. Pinheira |  | Done | Urgent |
| 12-12 | Create node mailing list “xxxx@gnss-epos.eu”. | R. Fernandes |  | In progress |  |
| 12-13 | Finish paper for Annals of Geophysics | R. Fernandes |  | Done | Urgent |
| 11th EB meeting – 10 Sept 2021 - Teleconference |  |  |  |  |  |
| 11-1 | Verify if UBI already received the money related to the MYCA from EPOS-ERIC. | R. Fernandes |  | Done | Received on 06/07/2021 |
| 11-2 | Check with their administrations the necessary procedures for receiving payments from UBI related to Governance and Coordination MYCA. | A. Socquet, C. Bruyninx and M. Vergnolle |  | Done |  |
| 11-3 | Check start date of MYCA. | R. Fernandes |  | Done | April 1, 2021 is the starting date; end date 31/12/2023 |
| 11-4 | Contact the UBI Administration to agree on how to carry out the payments to the third-party agencies and carry out the payments. | R. Fernandes |  | Done |  |
| 11-5 | Contact Lili to ask about the current status of the signature of the Service Contracts for next year. | R. Fernandes |  |  |  |
| 11-6 | Ask chair of SCC about the news related to service activation | C. Bruyninx |  | Done |  |
| 11-7 | Send email to EB mailing list to provide link to updated videos of Rui and Carine. | T. Pinheira |  | Done | Updated on November, 18 |
| 11-8 | Formally ask the CB to replace Machiel in the EB by another person proposed by the EB. | R. Fernandes |  | Done |  |
| 11-9 | Ask to correct the link to the Data Portal on the official EPOS web pages. | T. Pinheira |  | Done | Updated on November, 18 |
| 11-10 | Fix terminology issue for “operational nodes”. | Carine and Mathilde |  | Done |  |
| 11-11 | Update and clarify guidelines for the latest installation of the GLASS Node. | P. Crocker |  |  |  |
| 11-12 | Check with Jean Luc if the GLASS node mailing list can be changed to “xxxx@gnss-epos.eu”. | Mathilde |  | Done |  |
| 11-13 | Try to find someone to work regularly on the product portal. | R. Fernandes |  | Done |  |
| 11-14 | Try to find a solution to put the Product portal prototype developed by Machiel online as soon as possible. | R. Fernandes |  |  |  |
| 10th EB meeting – 24 June 2021 - Teleconference |  |  |  |  |  |
| 10-1 | Test latest version of Anubis in GLASS and ask nodes to start using it. | P. Crocker |  | Done | CB should ask Juliette about it |
| 10-2 | Update ICS web service documentation. | P. Crocker and EB |  | Done | Available from https://gnss-epos.eu/ics-tcs/ |
| 10-3 | Ask INGV who will replace Sergio | R. Fernandes |  | Done | INGV was contacted but still didn’t finish the hiring of the new person |
| 10-4 | Ask INGV and BKG about their plans to deliver the services they declared to EPOS | R. Fernandes |  | Done | Updated on December, 6 |
| 10-5 | Send a draft for the third-party agreements for the MYCA on governance to OCA, UGA and ROB. | R. Fernandes |  | Done | Not necessary for ROB |
| 10-6 | Make an outline of the paper for Annals of Geophysics | R. Fernandes | End of June 2021 | Done |  |
| 10-7 | Prepare the first draft of the article for the Annals of Geophysics | All |  | Done |  |
| 9th EB meeting – 7 April 2021 - Teleconference |  |  |  |  |  |
| 9-1 | Contact Antonio Avallone to clarify the INGV commitment to be a SP for software development. | R. Fernandes |  | Done |  |
| 9-2 | Update ICS turtle file. | P. Crocker |  | Done |  |
| 9-3 | Obtain https certificate for DGW | J.L. Menut |  | Done | Client server has the certificate, but not “GLASS API” server – not urgent since AAAI is not set up |
| 9-4 | Install latest version of GLASS at the Data Gateway. | J.L. Menut |  | Done |  |
| 9-5 | Provide the results of the DGW survey to Paul | M. Vergnolle |  | Done |  |
| 9.6 | Compile single document with survey results and provide it to the EB and CB (and ICS). | J. Manteigueiro & P. Crocker |  | Done | Forward mail sent to the ICS to Mathilde and Carine |
| 9-7 | Invite the representatives of the DPC and UFG to the next CB meeting. | R. Fernandes |  | Done |  |
| 9-8 | Propose to the EB updated content of our TCS pages on the official EPOS website. | T. Pinheira & R. Fernandes |  | NEW AI |  |
| 9-9 | Write skeleton of TCS paper and send it around for input. | R. Fernandes | By end of month | Done |  |
| 9-10 | Make short videos of overview of our TCS and product portal. | R. Fernandes & M. Bos |  | Not yet done |  |
| 8th EB meeting – 23 Feb. 2021 - Teleconference |  |  |  |  |  |
| 8-1 | Review the station metadata at the product portal. | M. Bos |  | In progress | Report at next EB |
| 8-2 | Improve the response time of the product portal. | M. Bos |  | In progress | Report at next EB |
| 8-3 | Inform participants to the webinar that videos and pdfs are online (https://gnss-epos.eu/webinar-2021/) and asks for questions that they would like to see answered. | R. Fernandes |  | Done |  |
| 8-4 | Send email to node managers advising to install new version of GLASS. | P. Crocker |  | Done |  |
| 8-5 | Prepare a document with a strategy for upgrading GLASS. | J.L. Menut & P. Crocker |  |  | Report at next EB |
| 8-6 | Install latest version of GLASS at the Data Gateway. | J.L. Menut |  | Done |  |
| 8-7 | Follow up the installation of the new version of GLASS in the nodes. | J.L. Menut & P. Crocker |  | Not done yet | Summer 2021: bug in related to last GLASS-API version reported to Paul : wait for the correction of GLASS API? Proposal: Ask each node manager the version of each software and report it |
| 8-8 | Organise a common meeting of developers and nodes. | J.L. Menut & P. Crocker |  |  | Report at next EB |
| 8-9 | Prepare questions for User Survey on GNSS portals. | C. Bruyninx, M. Vergnolle, M. Bos |  | Done |  |
| 8-10 | Write introductory text for User Survey on GNSS portals. | C. Bruyninx |  | Done |  |
| 8-11 | Have a Skype to discuss questions for User Survey on GNSS portals. | C. Bruyninx, M. Vergnolle, M. Bos, P. Crocker |  | Done |  |
| 8-12 | Send the User Survey email to the User Feedback Group. | R. Fernandes |  | Done |  |
| 8-13 | Contact Karin Kollo to set-up conference to decide on continuation of Estonian data node. | R. Fernandes |  | Done |  |
| 8-14 | Keep EB informed about GDPR-related discussions within the IGS. | C. Bruyninx |  | Done |  |
| 8-15 | Discuss with Jan Dousa how we can keep Anubis up to date in EPOS. | C. Bruyninx |  | Done |  |
| 6th EB meeting – 4 Dec. 2020 - Teleconference |  |  |  |  |  |
| 6-1 | Inform Anne how to access the gitlab of the pitches. | J.L. Menut |  | Done |  |
| 6-2 | Ask Jan Michalek for the list of tests used to validate our portals. | C. Bruyninx |  | Done | Taken over by P. Crocker and J. Manteigueiro |
| 6-3 | Contact User Feedback Group to participate in POT validation. | R. Fernandes |  | Done |  |
| 6-4 | Distribute draft of governance plan to CB. | R. Fernandes & M. Bos |  | Done |  |
| 6-5 | Send to EB the presentation of Kirsten Elger with information about DOI’s. | C. Bruyninx |  | Done |  |
| 6-6 | Announce the EPOS-GNSS webinar on the RENAG mailing list. | A. Socquet |  | Done |  |
| 6-7 | Distribute webinar program with session titles and hours. | R. Fernandes & M. Bos | Dec. 11, 2020 | Done |  |
| 6-8 | Provide outline of presentation at the EPOS-GNSS webinar and short description of its content. | All presenters | Dec. 18, 2020 | Done |  |
| 6-9 | Provide Power-Point presentation with audio to EB. | All presenters | Jan. 11, 2021 | Done |  |
| 6-10 | Organize a meeting with the GLASS developers | P. Crocker |  |  |  |
| 5rd EB meeting – 22 Oct. 2020 - Teleconference |  |  |  |  |  |
| 5-1 | Discuss authentication at Data Gateway. How to implement it? | P. Crocker & J.L. Menut | Next EB meeting | Done | Meeting organised by M. Vergnolle on 08/07/2021, attended by José, Paul, JL, Arthur |
| 5-2 | Provide velocities in ETRF2014 frame at Product Portal. | M. Bos |  | Done |  |
| 5-3 | Organize meeting with ICS | P. Crocker |  | Done | ICS-TCS workshop |
| 5-4 | Investigate how to back-up the whole EPOS GLASS network and a node. | P. Crocker & J.L. Menut |  | Not yet done | Report at next EB |
| 4rd EB meeting – 10 Sept. 2020 - Teleconference |  |  |  |  |  |
| 4-1 | Prepare text for organization of DPC | C. Bruyninx | End Sept. 2020 | Done |  |
| 4-2 | Setup CB meeting to approve the DPC proposal. | R. Fernandes |  | Done |  |
| 4-3 | Finalize text for moving stations from “proposed” to “included” in the EPOS network | C. Bruyninx | End Sept. 2020 | Done |  |
| 4-4 | Submit text on “Moving stations from proposed to included in the EPOS network” to the CB for approval. | R. Fernandes |  | Done by CB |  |
| 4-5 | Write documentation for Node manager on what to do after installing the GLASS software. | J.L. Menut |  | Done |  |
| 4-6 | Keep the EB and M3G informed about the status of the nodes | J.L. Menut | As soon as change occurs | Done |  |
| 4-7 | Create an API to get the latest updated site logs to facilitate the verification of the updates of this information at the DGW. | ROB |  | Done |  |
| 4-8 | Verify the correct updating of the site logs at the DGW after a site log update at M3G. | J.L. Menut |  | Done | Use instead the emails issued by ROB |
| 4-9 | Collect information on which node is linked to which station and make this information available to the DGW. | ROB |  | Done |  |
| 4-10 | Improve the visibility of the download button/procedure of data at the DGW. | J.L. Menut |  | Done | Report at next EB |
| 4-11 | Implement warning to GLASS managers when update/upgrade of GLASS software is required. | P. Crocker |  | Done | Email was sent |
| 4-12 | Make a proposal on how to correct in practice the misleading ‘stations with RINEX data’ on the ICS web site. | P. Crocker |  | In progress | To be checked once DGW has updated its GLASS version |
| 4-13 | Prepare doodle to fix the date of the next consortium board meeting. | R. Fernandes | ASAP | Done | Date fixed to 27th October 2020 from 9h30 to 13h30 (CET) |
| 4-14 | Get in touch with EPOS-ECO to get an answer of possible support for setting up webinars. | R. Fernandes | Early Oct. 2020 | Done |  |
| 3rd EB meeting – 24 June 2020 - Teleconference |  |  |  |  |  |
| 3-1 | Organise a new GLASS node meeting | J.L. Menut |  | Done |  |
| 3-2 | Check with Ambrus if the multi-year solution EPN densification already includes the INGV and UGA-CNRS solutions. | A. Socquet |  | Done |  |
| 3-3 | Contact EPOS ECO to see if money foreseen for organisation of Oct. meeting can be used in a different way, e.g. to hire a professional company to provide a technical support for the webinars. | R. Fernandes |  | Done |  |
| 3-4 | Prepare the agenda for the meeting in October by mid-July. | R. Fernandes | Mid July 2020 | Done |  |
| 3-5 | For next Node report, separate between stations with RINEX stations and those, which have no data. | J.L. Menut |  | Done |  |
| 3-6 | Adapt portal code to use station 9-char ID in the node portals | J.L. Menut |  | Done | GLASS-API still needs update! |
| 3-7 | Try to reduce insertion time of new stations into DB. | J.L. Menut S. Bruni |  | Done |  |
| 3-8 | Create place where bugs of unknown origin can be placed | J.L. Menut |  | Done |  |
| 3-9 | Organise a product meeting in July | A. Socquet | July 2020 | Done |  |
| 3-10 | Invite Paul to next EB meeting | C. Bruyninx |  | Done |  |
| 3-11 | Start the discussion on the service delivery plan | R. Fernandes |  | To Do | Report at next EB |
| 2nd EB meeting – 8 April 2020 - Teleconference |  |  |  |  |  |
| 2-1 | The EB should read the coordinator task descriptions for Secretariat and Outreach & Communications and send comments within 3 days. | EB |  | Done |  |
| 2-2 | Compile task descriptions of each coordinator in one document and send it to consortium board. | C. Bruyninx |  | Done | From where is the final document available? |
| 2-3 | Contact Ambrus to get ensure that the EUREF densification product becomes available at the DGW | A. Socquet M. Bos |  | Done | Time series not available yet |
| 2-4 | Coordinate with the nodes to update the GLASS software at the nodes. | J.L. Menut P. Crocker |  | Done |  |
| 2-5 | Send out Doodle to select date for general meeting. Distribute to CB dates for general meeting for people to save the date (26-28 of October 2020), including the days for CB and/or EB meeting. | R. Fernandes |  | Done |  |
| 2-6 | Write a consolidated document for the products. | A. Socquet M. Bos |  | In progress | Report at next EB |
| 2-7 | Send each 2 months to CB an update on new EPOS stations | C. Bruyninx | Bi-monthly | Done |  |
| 2-8 | Sends URL of maps with data availability to CB | C. Bruyninx |  | Done |  |
| 2-9 | Test RINEX 3 in GLASS | J.L. Menut P. Crocker J. Manteigueiro |  | Done |  |
| 2-10 | Ask the analysis centers about their capability to process RINEX 3. | A. Socquet |  | Done | ACs are ready, or will soon be ready |
| 1st EB meeting – 17 Feb. 2020 - Teleconference |  |  |  |  |  |
| 1-1 | Send an email to the CB to ask confirmation that Paul will continue to lead our TCS-ICS interaction. | C. Bruyninx |  | Done |  |
| 1-2 | Need to discuss who is responsible for monitoring of the data availability. | EB |  | Done |  |
| 1-3 | Invite Jean-Luc to next technical product meeting. | A. Socquet |  | Done |  |
| 1-4 | Prepare update of task descriptions of Secretariat and Outreach& Communications coordinator and present it at next EB | UBI |  | Done |  |
| 1-5 | Contact the service providers in charge of products to prepare a plan-B for the generation of the GNSS products in case no extra EPOS-ERIC funding will be provided. | A. Socquet |  | Done |  |
| 1-6 | Check if the GLASS-API problem is an access problem or a bug. If it is a bug, then he will get in touch with Paul. Juliette Legrand should be kept in the loop. | J.L. Menut |  | Done |  |
| 1-7 | Organize a teleconference with ROB, UBI and OCA about the setup of criteria for new GLASS nodes. Afterwards, the draft with rules will be sent to the CB. | J.L. Menut |  | Done |  |
| 1-8 | Check why the date of the site log update is not in the DB of the DGW. | J.L. Menut |  | Done |  |
| 1-9 | Look into the suggestions for improving the DGW. | J.L. Menut |  | Done |  |
| 1-10 | Inform Jean-Luc when a new release of the software is available. | P. Crocker |  | Done |  |
| 1-11 | Get prices for a 2+0.5 day meeting in Algarve, inform the CB, create a Doodle and afterwards send the plan to Massimo. | R. Fernandes |  | Done |  |
| 1-12 | Contribute to the document providing TCS priorities for updating the ICS-C web portal. | R. Fernandes P. Crocker |  | Done |  |
| 1-13 | Prepare a web page on the EPOS-GNSS web site, maintained by UBI, including links to documentation/guidelines/letters related to data provision, nodes, products, and software. | M. Bos |  | Done |  |
| 1-14 | Set up doodles for next EB meetings. | C. Bruyninx |  | Done |  |